## Sheet1
|  | Afhankelijk van | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Deadline
Start | [12 empty] | Werken
1 | Introductie | bar: Week 1
2 | Samenwerkingscontract | 1 | bar: Week 1
3 | Website opstarten | 1 | bar: Week 1
4 | Vragen projectleider | 1 | bar: Week 2
Projectgroep
5 | Groep samenstellen | 1 | bar: Week 1
6 | Zelfevaluatie | bar: Week 5; Week 10
Projectleider
7 | Sander | 5 | bar: Week 1 to Week 3
8 | Kirty | 5 | bar: Week 4 to Week 6
9 | Justin | 5 | bar: Week 7 to Week 9
Workshop volgen
10 | Sander | bar: Week 2
11 | Kirty | bar: Week 4 to Week 5
12 | Justin | bar: Week 3
13 | Aantekeningen | 10, 11, 12 | bar: Week 2 to Week 5
14 | Samenvatting | 10, 11, 12 | bar: Week 2 to Week 5
Onderzoeken
15 | Sensoren | bar: Week 3 to Week 4
16 | Marcolax | bar: Week 3
17 | Fischer Technik | bar: Week 4
Ontwerpen
18 | Robot | 19, 20 | bar: Week 3 to Week 5
19 | Laadruimte | bar: Week 3 to Week 4
20 | Fischer Technik of Marcolax | Onderzoek | bar: Week 3 to Week 4
Voorbereiding
22 | Voortgangsrapportage | 12, 13, 14, 15, 16 | bar: Week 2 to Week 9
23 | Offerte | bar: Week 2 to Week 6
24 | Testverslag | 14, 15, 16 | bar: Week 5
Realisatie
25 | Website | bar: Week 2 to Week 9
26 | Samenwerkingscontract | 1 | bar: Week 1
27 | Code Robot | 18 | bar: Week 8
28 | Challenge | bar: Week 10